## WEEK1
Sprint Burndown Chart
António Palmeirim 63667, Duarte Inácio 62397, André Santos 62331, Tiago Santos 63390, Luis Serrano 60253, Rafeal Tavares 60608
Task ID | Task Description | Initial Estimate
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Play and study the game for the first time | 3 | 1 | 1 |  |  |  | 0.5 | 0.5
2 | Reunite with group and discuss game mechanics | Initial Estimate Day 0: 0.5; Initial Estimate Day 3: 0.5
3 | Create first User Story | Initial Estimate Day 0: 0.5; Initial Estimate Day 4: 0.5
4 | Review first User Story | Initial Estimate Day 0: 0.25; Initial Estimate Day 4: 0.25
5 | Create second User Story | Initial Estimate Day 0: 0.5; Initial Estimate Day 4: 0.25; Initial Estimate Day 5: 0.25
6 | Review second User Story | Initial Estimate Day 0: 0.25; Initial Estimate Day 5: 0.25
7 | Create third and last User Story | Initial Estimate Day 0: 0.5; Initial Estimate Day 5: 0.5
8 | Review third User Story | Initial Estimate Day 0: 0.25; Initial Estimate Day 5: 0.25
9 | Create fourth User Story | Initial Estimate Day 0: 0.5; Initial Estimate Day 6: 0.5
10 | Review fourth User Story | Initial Estimate Day 0: 0.25; Initial Estimate Day 6: 0.25
11 | Review all User Stories and confirming our selection of US | Initial Estimate Day 0: 1; Initial Estimate Day 6: 0.5; Initial Estimate Day 7: 0.5
12 |  | Initial Estimate Day 0: 0
13 |  | Initial Estimate Day 0: 0
14 |  | Initial Estimate Day 0: 0
Completed Effort |  | 0 | 1 | 1 | 0.5 | 1 | 1.25 | 1.75 | 1
Remaining Effort |  | 7.5 | 6.5 | 5.5 | 5 | 4 | 2.75 | 1 | 0
Ideal Burndown |  | 7.5 | 6.4286 | 5.3571 | 4.2857 | 3.2143 | 2.1429 | 1.0714 | 0