## WEEK1
Sprint Burndown Chart
António Palmeirim 63667, Duarte Inácio 62397, André Santos 62331, Tiago Santos 63390, Luis Serrano 60253, Rafeal Tavares 60608
Task ID | Task Description | Initial Estimate
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Define the work plan | Initial Estimate Day 0: 1; Initial Estimate Day 1: 0.5; Initial Estimate Day 2: 0.5
2 | Create code smells | Initial Estimate Day 0: 2; Initial Estimate Day 2: 1; Initial Estimate Day 3: 0.5; Initial Estimate Day 4: 0.5
3 | Review Code smells | Initial Estimate Day 0: 0.5; Initial Estimate Day 4: 0.5
4 | Create patterns | Initial Estimate Day 0: 3; Initial Estimate Day 3: 1; Initial Estimate Day 4: 2
5 | Review patterns | Initial Estimate Day 0: 0.5; Initial Estimate Day 4: 0.5
6 | Create Code Metrics | Initial Estimate Day 0: 3; Initial Estimate Day 4: 1.5; Initial Estimate Day 5: 1.5
7 | Review Code Metrics | Initial Estimate Day 0: 0.5; Initial Estimate Day 5: 0.5
8 | Create Use Case Diagram | Initial Estimate Day 0: 2; Initial Estimate Day 4: 0.5; Initial Estimate Day 5: 1.5
9 | Review use case diagram | Initial Estimate Day 0: 0.5; Initial Estimate Day 5: 0.5
10 | Document code smells, patterns, code metrics and use case diagram | Initial Estimate Day 0: 3; Initial Estimate Day 5: 1; Initial Estimate Day 6: 1; Initial Estimate Day 7: 1
11 | Review all and confirming our selection of everything | bar: Initial Estimate Day 0; Initial Estimate Day 7
12 |  | Initial Estimate Day 0: 0
13 |  | Initial Estimate Day 0: 0
14 |  | Initial Estimate Day 0: 0
Completed Effort |  | 0 | 0.5 | 1.5 | 1.5 | 5.5 | 5 | 1 | 2
Remaining Effort |  | 17 | 16.5 | 15 | 13.5 | 8 | 3 | 2 | 0
Ideal Burndown |  | 17 | 14.5714 | 12.1429 | 9.7143 | 7.2857 | 4.8571 | 2.4286 | 0