## WEEK1
Sprint Burndown Chart
António Palmeirim 63667, Duarte Inácio 62397, André Santos 62331, Tiago Santos 63390, Luis Serrano 60253, Rafeal Tavares 60608
Task ID | Task Description | Initial Estimate
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Define the work plan | Initial Estimate Day 0: 0.5; Initial Estimate Day 1: 0.5
2 | Redoing all of the Use Cases | Initial Estimate Day 0: 3.5; Initial Estimate Day 3: 1.5; Initial Estimate Day 4: 1; Initial Estimate Day 5: 1
3 | Adding visualisation graphic to all the metrics documents | Initial Estimate Day 0: 0.5; Initial Estimate Day 2: 0.5
4 | Reviewing the new Use Cases | Initial Estimate Day 0: 1; Initial Estimate Day 6: 0.5; Initial Estimate Day 7: 0.5
5 | Working on US2 (with corresponding pair) | 2 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5
6 | Working on US3 (with corresponding pair) | Initial Estimate Day 0: 2; Initial Estimate Day 6: 0.5; Initial Estimate Day 7: 1.5
7 | Working on US4 (with corresponding pair) | Initial Estimate Day 0: 2; Initial Estimate Day 5: 0.5; Initial Estimate Day 6: 0.5; Initial Estimate Day 7: 1
8 |  | Initial Estimate Day 0: 0
9 |  | Initial Estimate Day 0: 0
10 |  | Initial Estimate Day 0: 0
11 |  | Initial Estimate Day 0: 0
12 |  | Initial Estimate Day 0: 0
13 |  | Initial Estimate Day 0: 0
14 |  | Initial Estimate Day 0: 0
Completed Effort |  | 0 | 0.5 | 0.5 | 1.5 | 1.5 | 2 | 2 | 3.5
Remaining Effort |  | 11.5 | 11 | 10.5 | 9 | 7.5 | 5.5 | 3.5 | 0
Ideal Burndown |  | 11.5 | 9.8571 | 8.2143 | 6.5714 | 4.9286 | 3.2857 | 1.6429 | 0