## WEEK1
Sprint Burndown Chart
António Palmeirim 63667, Duarte Inácio 62397, André Santos 62331, Tiago Santos 63390, Luis Serrano 60253, Rafeal Tavares 60608
Task ID | Task Description | Initial Estimate
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Plan for the upcoming sprint. | Initial Estimate Day 0: 0.5; Initial Estimate Day 1: 0.5
2 | Identify and prioritize User Stories for implementation. | Initial Estimate Day 0: 1; Initial Estimate Day 1: 0.5; Initial Estimate Day 2: 0.5
3 | Collaborate with assigned team members to start implementation. | Initial Estimate Day 0: 2; Initial Estimate Day 1: 1; Initial Estimate Day 2: 1
4 | Begin adapting code for the assigned User Stories. | Initial Estimate Day 0: 3; Initial Estimate Day 1: 1; Initial Estimate Day 2: 1; Initial Estimate Day 3: 1
5 | Address and incorporate feedback. | bar: Initial Estimate Day 0; Initial Estimate Day 3
6 | Ensure correct code structure. | Initial Estimate Day 0: 2; Initial Estimate Day 3: 1; Initial Estimate Day 4: 0.5; Initial Estimate Day 5: 0.5
7 | Prepare for the upcoming sprint review. | Initial Estimate Day 0: 0.5; Initial Estimate Day 4: 0.5
8 | Ensure all completed User Stories are ready for entire team review. | Initial Estimate Day 0: 0.5; Initial Estimate Day 4: 0.5
9 | Communicate progress and challenges to the team. | Initial Estimate Day 0: 0.5; Initial Estimate Day 4: 0.5
10 | Collaborate with team members to address any impediments. | Initial Estimate Day 0: 1; Initial Estimate Day 5: 0.5; Initial Estimate Day 6: 0.5
11 | Review and update the overall project work plan. | Initial Estimate Day 0: 1; Initial Estimate Day 5: 0.5; Initial Estimate Day 6: 0.5
12 | Adjust tasks and timelines as needed. | Initial Estimate Day 0: 0.5; Initial Estimate Day 6: 0.5
13 | Prepare for the sprint retrospective. | Initial Estimate Day 0: 0.5; Initial Estimate Day 7: 0.5
14 | Gather feedback on the sprint process. | Initial Estimate Day 0: 0.5; Initial Estimate Day 7: 0.5
Completed Effort |  | 0 | 3 | 2.5 | 3 | 2 | 1.5 | 1.5 | 1
Remaining Effort |  | 14.5 | 11.5 | 9 | 6 | 4 | 2.5 | 1 | 0
Ideal Burndown |  | 14.5 | 12.4286 | 10.3571 | 8.2857 | 6.2143 | 4.1429 | 2.0714 | 0