## Sheet1
Sprint Burndown Chart
António Palmeirim 63667, Duarte Inácio 62397, André Santos 62331, Tiago Santos 63390, Luis Serrano 60253, Rafeal Tavares 60608
Task ID | Task Description | Initial Estimate
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Plan for the upcoming sprint. | Initial Estimate Day 0: 0.5; Initial Estimate Day 1: 0.5
2 | See what user stories are better developed and focus on fixing problems. | bar: Initial Estimate Day 0 to Initial Estimate Day 1
3 | Collaborate with assigned team members to continue implementation. | Initial Estimate Day 0: 2; Initial Estimate Day 1: 0.5; Initial Estimate Day 2: 1; Initial Estimate Day 3: 0.5
4 | Try to find solutions to specific dificulties. | Initial Estimate Day 0: 1; Initial Estimate Day 3: 0.5; Initial Estimate Day 4: 0.5
5 | Report creation and template design. | bar: Initial Estimate Day 0; Initial Estimate Day 3
6 | Divide the report work between team members. | Initial Estimate Day 0: 0.5; Initial Estimate Day 4: 0.5
7 | Midweek gathering to ensure work is working as supposed. | Initial Estimate Day 0: 1.5; Initial Estimate Day 4: 1.5
8 | Ensure every User Story is completed. | Initial Estimate Day 0: 0.5; Initial Estimate Day 4: 0.5
9 | Finish report. | Initial Estimate Day 0: 2.5; Initial Estimate Day 5: 1; Initial Estimate Day 6: 1.5
10 | Gathering to plan the video. | bar: Initial Estimate Day 0; Initial Estimate Day 5
11 | Adjust tasks and timelines as needed. | Initial Estimate Day 0: 0.5; Initial Estimate Day 4: 0.5
12 | Finish the video. | Initial Estimate Day 0: 2; Initial Estimate Day 5: 0.5; Initial Estimate Day 6: 1; Initial Estimate Day 7: 0.5
13 | Verifiy all the work is done. | Initial Estimate Day 0: 0.5; Initial Estimate Day 7: 0.5
14 | Gather feedback on the sprint process. | Initial Estimate Day 0: 0.5; Initial Estimate Day 7: 0.5
15 | Upload SCRUM and Burndown information. | Initial Estimate Day 0: 0.5; Initial Estimate Day 7: 0.5
Completed Effort |  | 0 | 2 | 1 | 2 | 3.5 | 2.5 | 2.5 | 2
Remaining Effort |  | 15.5 | 13.5 | 12.5 | 10.5 | 7 | 4.5 | 2 | 0
Ideal Burndown |  | 15.5 | 13.2857 | 11.0714 | 8.8571 | 6.6429 | 4.4286 | 2.2143 | 0